## Sheet1
Risk Assessment |  |  |  |  | Control Measures
Description | Evaluation | Risk | Impact | Responsibility | Currently | Proposed | Response
Virtual Machine web server goes down | Will result in down time for the website. However no date will be lost and could easily move to another platform | Low | Low | Google Cloud Platform | All code is saved on another platform so can still access the code if the server goes down. | Create cloned VM backup with all modules ready to deploy. | Make the users aware of the situation and ask them to be patient as we will have th web site up and running soon.
Virtual Maching for SQL server goes down | Will result in users being temporary cut off form some aspects of the website | Low | Medium | Google Cloud Platform |  | Take back-ups every hour | Make the users aware of the situation and ask them to be patient as we will have th web site up and running soon.
SQL Injection which exploits SQL statements | Will result in a data breach of the users personal information | Low | High | Pranay Wara | Passwords are hashed so the intruders will need to decrypt the passwords | Using a password longer then 7 characters and telling the user to use a unique password | Tell the users about the data breach and urge them to chage there password
Phising attacks | Will result in a data breach of the users personal information | Low | High | Pranay Wara | Any suspect emails or links will be moved to the spam area on emails |  | Tell the users about the data breach and urge them to chage there password
Social Engineering attack | Will result in a data breach of the users personal information | Low | High | Pranay Wara | Don’t trust anyone online with any sensitive information |  | Tell the users about the data breach and urge them to chage there password
Sharing senstive information on github | Allowing external people access to the database which could result in deleting or changing the database | Low | High | Pranay Wara | Only accessing the database from my home computer which is a secure location |  | Tell the users about the data breach and urge them to chage there password
Giving sudo abilities to Jenkins | Allowing external systems to install anything on to the Jenkins VM | Medium | Medium | Pranay Wara | Only Jenkins is able to access the VM. |  | Wouldn’t disrupt the customer as it will only disrupt the testing.